## Sheet1
Task | Start week | End week | Duration(week)
Information searching ( table design, algorithm) | 1 | week1 | 1
Database Table design | 2 | week2 | 1
Algorithm Design | 3 | week3 | 1
Information searching ( loading data,filter the data) | 4 | week4 | 1
loading data(including data filter) | 5 | week6 | 2
Disaster Recovery( base on the loading time) | 7 | week7 | 1
Functional requirement implement | 8 | week9 | 1
Information searching( data visualization) | 9 | week9 | 1
Data visualization | 10 | week10 | 1
Task | Start week | End week | Duration(week)
Task | Start week | End week | Duration(week)
Implementation Plan | 7-Fall | 8 | 1
Design Document | 8-Fall | 10
Database Table Implement | 1-winter | week 1 (winter term) | 1
Data loading for checking table | 2-winter | week 3 (winter term) | 2
Functional requirement Implement(insert,search and sort) | 4-winter | week 5 (winter term) | 2
Functional requirement Implement (aggregation) | 6-winter | week 8 (winter term) | 2
Data visualization | 9-winter | week 10 (winter term) | 2
Test for functionality | 1-spring | 2-spring | 2
Performance Optimization | 3-spring | 5-spring | 2
Security Optimization | 5-spring | 7-spring | 2
Task | Start week | End week | Duration(days)
Implementation Plan | 7-Fall | week8 | 1
Design Document | 8-Fall | week10 | 3
Database Table Implementation | 1-Winter | week 1 (winter term) | 1
Data loading for checking table | 2-Winter | week 3 (winter term) | 2
Functional requirement Implementation(insert,search and sort) | 4-Winter | week 5 (winter term) | 2
Functional requirement Implementation(aggregation) | 6-Winter | week 8 (winter term) | 3
Data visualization | 9-Winter | week 10 (winter term) | 2
Test for functionality | 1-Spring | 2-spring | 2
Performance Optimization | 3-Spring | 4-spring | 2
Security Optimization | 5-Spring | 5-spring | 1
Cost Comparison | 6-Spring | 7-spring | 1